## Dashboard
State project approvals tracker
DTP State Project Concierge
Updates to be highlighted yellow. Fortnightly proponent updates in red text. Fortnightly regulator updates in purple text. Agreed updates in black.
RIsk Indicators: |  | Certain Impact | Likely Impact | On Schedule | Closed Out
[6 empty] | Draft Documents |  |  |  | Documents for Approval | [7 empty] | NOTE: Please include date and commenting org in comment. E.g. "11/01/23 (DTP): Comment contents"
Project | Proponent / Alliance | Approving Regulator Unit | Application/Item | Stage | Overall Status | Draft Forecast Submission | Draft Actual Submission | Draft comments due | Draft review comments issued | Target Submission Date | Forecast submission date | Actual submitted date | RFI requested date | RFI due date | RFI received date | Target Approval date | Actual approval date | Regulator Comments | OCG Comments | Forecast Start Construction date | Forecast Construction Completion date

## Notes
Notes: State Project Approvals Tracker DTP State Project Concierge
Guidance notes:
Application: | The State Projects Approvals Tracker should be used to track and monitor state projects or programs that require complex approvals.
Proponent updates: | Proponents should complete the template with dates including expected lodgement dates, approval dates and construction start dates. Proponents should discuss approval dates with DTP to ensure dates can be agreed.
Agreed dates: | DTP and proponents agree the dates set out in the approval tracker.
Updates: | Updates to forecast dates should be discussed and agreed with DTP. DTP recommends establishing regular meetings to discuss changes. For complex projects, weekly or fortnightly meetings may be appropriate.
Tracking changes: | Dates which are amended should be struck out to ensure changes are recorded.
Comments: | Comments should refer to the reason dates were changed, and the date of the change. For example "02/02/22 - Forecast lodgement date brought forward to align with new construction start date".
Red rated risks: | The delivery schedule is/will be impacted by approvals.
Amber rated risks: | There is a strong likelihood the delivery schedule will be impated by the approvals.
Clear: | The approvals program is running to schedule.