# Resource 1: Work program

The following table can be used to develop an overall timeframe for the project.

| Step or Task | Notes | Commence date | Completion date |
| --- | --- | --- | --- |
| Step 1: Preparation |  |  |  |
| 1.1: Audit of legacy study | See notes for 1.3 |  |  |
| 1.2: Audit of planning controls | See notes for 1.3 |  |  |
| 1.3: Council tasks | May be desirable or more efficient to undertake some of these tasks before commencing 1.1 and 1.2. Alternatively, the three tasks could be undertaken simultaneously. |  |  |
| 1.4: Prioritising review work | If required. Requires 1.1 and 1.2 to be completed |  |  |
| Step 2: Undertaking the review |  |  |  |
| 2.1: Preparing the brief | Allow sufficient time for consultants to respond to the tender invitation. Avoid periods such as EOFY or just prior to Xmas-New Year. |  |  |
| 2.2: Appointing the heritage consultant | Allow time to check references and make enquiries as desirable to confirm the preferred consultant and for consultant interviews, if required. |  |  |
| 2.3: Managing the project | This is an ongoing task throughout this stage. It includes the preparation of meeting agendas and minutes, coordinating consultation activities and managing internal governance processes. |  |  |
| 2.4: Reviewing draft citations | This is an opportunity to correct errors before the citations are circulated. Ensure sufficient time is allowed for this task. |  |  |
| 2.5: Stakeholder consultation | This will commence once the draft citations have been reviewed by council and updated as required. |  |  |
| 2.6: Responding to submissions | Time required for this task will depend upon the number of submissions and the issues raised by them. Final changes to the draft citations are made. |  |  |
| 2.7: Adoption of the updated study by council | Allow time for: - Consultant to prepare final report and then draft PSA documentation - The PCG to review the final report - The DTP Regional Planning Services regional office to review the study and PSA documents in relation to VLHG and the MDFC requirements (Suggest allowing a minimum two-week period for the DTP regional office to respond) - Council reporting. |  |  |
| Step 3: Implementing the review |  |  |  |
| 3.1: Planning Scheme Amendment | Preparation of final PSA documentation. Allow time for: - Creation of PSA in ATS and authoring changes to planning scheme ordinance and uploading supporting information - Requesting PSA map changes via DTP mapping services - Council reporting and responding to any conditions or changes required as part of authorisation. For further information about timelines for preparing and processing a PSA see chapter 2.4 of ‘Using Victoria’s Planning System’ |  |  |
| 3.2: Amendment exhibition and consultation | Allow time for preparation and to give notice to affected landowners, land managers and statutory authorities (exhibition period is usually a minimum of four weeks) |  |  |
| 3.3: Responding to submissions | Difficult to estimate timing in advance, as it will depend on the number and nature of submissions. Allow time for council reporting. |  |  |
| 3.4: Panel hearing | Allow time for appointment of panel, panel hearing and preparation of Panel report (usually finalised 20-40 days after the hearing). |  |  |
| 3.5: Approval and final updates | Allow time for council reporting. |  |  |